## README
Quotation Generator — Pre-Launch QA Test Case Suite
Generated from a full source-code audit (backend controllers/models, Zoho integration, email service, frontend pages/components) to cover every crucial flow before go-live.
HOW TO USE THIS WORKBOOK
- Each tab is a functional module. Work through tabs in the 'Suggested Execution Order' below.
- Fill 'Actual Result' and set 'Status' (Not Run / Pass / Fail / Blocked / N/A) as you execute.
- 'Priority' = Critical (must pass before go-live, blocks launch) / High / Medium / Low.
- 'Type' = Functional / Negative / Edge Case / Security / Concurrency / Performance / UI/UX / Regression / Integration.
- Rows marked Security or Concurrency are the highest-value tests found during the audit — this app has ZERO automated
tests today, so this manual pass is the only safety net before production traffic hits it.
- Test directly against the API (Postman/curl) where noted, not just through the UI — several validation rules exist
only client-side and must be independently confirmed on the server.
KEY RISK AREAS CALLED OUT BY THE AUDIT (give these extra attention):
1. ViewQuotationScreen.jsx and the status-transition logic in quotationController.js — largest recent change (+1185 lines),
hand-coded per-role status transitions (not a formal state machine) = highest regression risk.
2. Award -> Zoho estimate creation — hardcoded per-company tax ID maps, complex domestic/GCC tax branching, and the
Zoho call MUST succeed before the DB is updated. A 4th company added without updating the tax map fails silently.
3. Email cycle (brand new, ~500 lines) — fire-and-forget, never throws, silently no-ops if Graph credentials are
missing. Must be verified end-to-end per role transition or failures will go unnoticed until users complain.
4. Review Comments (brand-new highlight/annotate feature) — text-anchoring can break silently if content is edited.
5. Desktop (QuotationLayout.jsx) vs Mobile (MobileQuotationLayout.jsx) are two independently maintained renderers —
any pricing/VAT/formatting fix must be verified on BOTH.
6. Currency formatting — 9 currencies, 3 of which (KWD/BHD/OMR) use 3 decimal places instead of 2.
7. No automated tests exist anywhere in the repo — this spreadsheet is the sole pre-launch safety net.
SUGGESTED EXECUTION ORDER
1. Auth & Access Control 6. Quotation Editing & Status Transitions 11. PDF Generation & Print
2. User Management (Admin) 7. Approval Workflow (Ops + Admin) 12. Email Notifications
3. Company Management 8. Award & Zoho Estimate 13. Currency & Exchange Rates
4. Customer Management 9. Cancel / Revise / Amend / Duplicate 14. In-App Notifications
5. Item Catalog & Zoho Sync 10. Review Comments 15. Security, Resilience & Performance
16. Mobile & Cross-Browser
TOTAL TEST CASES: 225 across 17 modules
MODULE BREAKDOWN
Auth & Access Control: 21 test cases
User Management: 11 test cases
Company Management: 9 test cases
Customer Management: 22 test cases
Item Catalog & Sync: 5 test cases
Quotation Creation: 20 test cases
Quotation Edit-Status: 15 test cases
Approval Workflow: 13 test cases
Award & Zoho: 23 test cases
Cancel-Revise-Amend: 12 test cases
Review Comments: 9 test cases
PDF Generation: 17 test cases
Email Notifications: 15 test cases
Currency & Exchange: 7 test cases
In-App Notifications: 6 test cases
Security & Resilience: 14 test cases
Mobile & Cross-Browser: 6 test cases

## Auth & Access Control
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
AUTH-001 | Auth | Critical | Functional | Register new user with valid data | App accessible, no account with given email | 1. Go to Register 2. Fill name/email/phone/password (>=6 chars) 3. Submit | email: newuser@test.com, password: Passw0rd | Account created with role='user' regardless of any hidden role field; redirected to login/home |  | Not Run
AUTH-002 | Auth | High | Negative | Register with duplicate email | An account already exists with the email | 1. Register with an email already in use | existing email | Server rejects with clear 'email already exists' error; no duplicate user created |  | Not Run
AUTH-003 | Auth | High | Negative | Register with duplicate phone | Account exists with the phone number | 1. Register new account reusing an existing phone number | existing phone | Rejected with duplicate-phone error |  | Not Run
AUTH-004 | Auth | Medium | Negative | Register with password < 6 chars | - | 1. Submit registration with a 5-character password | password: abcde | Rejected client-side and server-side (400) with min-length message |  | Not Run
AUTH-005 | Auth | Critical | Security | Attempt role escalation at registration via direct API call | - | 1. POST /api/auth/register with body including role:'admin' (bypassing UI) | {..., role:'admin'} | User is created with role forced to 'user' server-side; admin role NOT granted |  | Not Run
AUTH-006 | Auth | Critical | Functional | Login with valid credentials | Active account exists | 1. Enter correct email/password 2. Submit | valid creds | JWT issued, redirected to role-appropriate dashboard (user/ops_manager/admin) |  | Not Run
AUTH-007 | Auth | High | Negative | Login with wrong password | Active account exists | 1. Enter correct email, wrong password | - | 401 with generic 'invalid credentials' (no user-enumeration hint) |  | Not Run
AUTH-008 | Auth | Critical | Negative | Login to a deactivated account | Admin has toggled isActive=false for a user | 1. Attempt login with that user's correct credentials | deactivated user creds | Login rejected even though password is correct; clear 'account deactivated' message |  | Not Run
AUTH-009 | Auth | High | Security | Brute-force login rate limiting | - | 1. Submit 21+ failed login attempts from same IP within 15 min | wrong password x21 | After 20 attempts, further attempts from that IP are rate-limited (429) regardless of account |  | Not Run
AUTH-010 | Auth | Medium | Edge Case | Rate limiter does not block successful logins | - | 1. Perform 25 successful logins in a row from same IP | valid creds | Rate limiter should skip counting successful requests; no lockout of legitimate rapid logins |  | Not Run
AUTH-011 | Auth | High | Functional | Forgot/reset password with valid token | User requested password reset | 1. Request reset 2. Use valid token+new password on reset endpoint | valid unexpired token | Password updated; user can log in with new password; old password no longer works |  | Not Run
AUTH-012 | Auth | High | Negative | Reset password with expired token | Reset token issued >expiry window ago | 1. Attempt reset using expired token | expired token | Rejected with token-expired error; password unchanged |  | Not Run
AUTH-013 | Auth | Medium | Negative | Reset password with tampered/invalid token | - | 1. Modify token string and submit reset | invalid token | Rejected, no password change, no stack trace leaked to client |  | Not Run
AUTH-014 | Auth | Medium | Functional | Update own profile details | Logged in | 1. Go to profile, update name/email/phone 2. Save | - | Profile updated; email/phone uniqueness still enforced against other users |  | Not Run
AUTH-015 | Auth | Medium | Functional | Update own password (self-service) | Logged in, knows current password | 1. Enter current + new password (>=6 chars) 2. Submit | - | Password updated; subsequent logins require new password |  | Not Run
AUTH-016 | Auth | Medium | Negative | Update password with wrong current password | Logged in | 1. Enter incorrect current password + valid new password | - | Rejected; password not changed |  | Not Run
AUTH-017 | Auth | Medium | Functional | Force change password after admin-generated temp password | Admin generated a temp password for user (mustChangePassword=true) | 1. Login with temp password 2. Verify forced redirect to change-password screen 3. Set new password | - | User cannot access app until password is changed; after change, mustChangePassword flag clears |  | Not Run
AUTH-018 | Auth | Medium | Functional | GET /api/auth/ops-managers accessible to any authenticated role | Logged in as 'user' role | 1. Trigger notify-manager list while creating a quotation | - | Returns list of active ops managers regardless of caller's own role |  | Not Run
AUTH-019 | Auth | Critical | Security | Expired/invalid JWT is rejected on protected routes | - | 1. Call any /api/* protected endpoint with an expired or malformed JWT | tampered/expired token | 401 Unauthorized, no data returned |  | Not Run
AUTH-020 | Auth | High | Security | JWT for a deactivated user is rejected mid-session | User logged in, then admin deactivates the account | 1. Admin deactivates user while user has a valid unexpired token 2. User makes a request | - | Request rejected (401) even though token itself hasn't expired — protect middleware re-checks isActive |  | Not Run
AUTH-021 | Auth | Low | Boundary | JWT_SECRET boot guard (env/infra check) | - | 1. Attempt to boot backend with JWT_SECRET shorter than 32 chars in the target environment config | - | Server refuses to start (fail-fast) rather than running insecurely — verify prod .env passes this check |  | Not Run

## User Management
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
UM-001 | User Management | High | Functional | Admin lists all users | Logged in as admin | 1. Go to User Management | - | All users listed with role/status/created date |  | Not Run
UM-002 | User Management | Critical | Security | Non-admin cannot access user management endpoints | Logged in as 'user' or 'ops_manager' | 1. Call GET/PUT/DELETE /api/auth/users* directly via API | - | 403 Forbidden for every admin-only endpoint |  | Not Run
UM-003 | User Management | High | Functional | Admin changes a user's role | Admin logged in, target user exists | 1. Change role from user -> ops_manager 2. Save | role: ops_manager | Role updated; user immediately gains ops_manager permissions on next request |  | Not Run
UM-004 | User Management | Medium | Negative | Admin sets an invalid role value | Admin logged in | 1. PUT /users/:id/role with role='superadmin' via direct API | role: superadmin | Rejected — role restricted to enum user¦admin¦ops_manager |  | Not Run
UM-005 | User Management | High | Functional | Admin toggles a user's active status | Admin logged in | 1. Deactivate an active user 2. Reactivate | - | isActive flips; deactivated user is immediately blocked from login/API access |  | Not Run
UM-006 | User Management | Critical | Negative | Admin attempts to delete self | Logged in as admin | 1. Attempt to delete own account | - | Blocked with clear error; account not deleted |  | Not Run
UM-007 | User Management | Critical | Negative | Admin attempts to delete a user referenced on quotations | Target user is createdBy/approvedBy/opsApprovedBy/awardedBy on >=1 quotation | 1. Attempt to delete that user | - | 400 error listing counts of referencing quotations by role; user not deleted |  | Not Run
UM-008 | User Management | Medium | Functional | Admin deletes a user with no quotation references | Target user has never created/approved/awarded anything | 1. Delete user | - | User deleted successfully |  | Not Run
UM-009 | User Management | High | Functional | Admin sets a specific password for a user | Admin logged in | 1. Use 'set password' action, enter new password | password: NewPass123 | User can log in with the new password immediately |  | Not Run
UM-010 | User Management | Medium | Functional | Admin generates a temp password | Admin logged in | 1. Click 'generate temp password' for a user | - | Random password generated & shown once; mustChangePassword=true set; user forced to change on next login |  | Not Run
UM-011 | User Management | Medium | Edge Case | Admin edits own role/status | Logged in as admin | 1. Attempt to demote own role or deactivate own account | - | Verify whether this is blocked or allowed — if allowed, confirm admin isn't instantly locked out mid-session unexpectedly |  | Not Run

## Company Management
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
COMP-001 | Company Mgmt | High | Functional | Admin creates a new company | Admin logged in | 1. Fill company name/code/baseCurrency/acceptedCurrencies/bankDetails 2. Save | code: TESTCO | Company created; appears in company selector across the app |  | Not Run
COMP-002 | Company Mgmt | High | Negative | Create company with duplicate code | A company with the same code exists | 1. Attempt to create another company using the same 'code' | duplicate code | Rejected — code must be unique (case-insensitive since it's uppercased) |  | Not Run
COMP-003 | Company Mgmt | High | Negative | Create company with duplicate zohoOrganizationId | A company already linked to that Zoho org | 1. Attempt to link a second company to the same zohoOrganizationId | duplicate org id | Rejected — zohoOrganizationId unique+sparse constraint enforced |  | Not Run
COMP-004 | Company Mgmt | Medium | Functional | Company slug auto-generated when omitted | - | 1. Create company without explicitly setting slug | name only | Slug auto-derived from name and is unique |  | Not Run
COMP-005 | Company Mgmt | Medium | Functional | Admin bulk-imports companies | Admin logged in, valid import file | 1. Use bulk import feature with a file containing several companies | valid bulk file | All valid rows imported; invalid rows reported without aborting the whole batch |  | Not Run
COMP-006 | Company Mgmt | High | Functional | Admin toggles company active status | Company exists and is in use | 1. Deactivate a company that has existing quotations/customers | - | Company marked inactive; verify companyContext middleware then rejects it (403) for new quotation/customer creation while historical data remains viewable |  | Not Run
COMP-007 | Company Mgmt | Critical | Functional | 4th/new company awarding without Zoho tax map entry | New company created with a zohoOrganizationId NOT present in the hardcoded TAX_IDS map | 1. Create + approve + award a quotation for this new company | - | Either the system clearly blocks award with a configuration error, OR flags to devs that it silently falls back to an unrelated org's tax IDs (known code risk) — verify actual behavior and file a bug if it silently falls back |  | Not Run
COMP-008 | Company Mgmt | Medium | Negative | companyId='all' rejected on customer/quotation create | - | 1. Attempt to create a customer/quotation with companyId literal 'all' or 'ALL' | companyId: all | Rejected — 'all' is a UI aggregate value only, not a real company |  | Not Run
COMP-009 | Company Mgmt | Medium | Functional | Non-admin cannot create/edit/delete companies | Logged in as user/ops_manager | 1. Attempt company CRUD via API directly | - | 403 for all mutating endpoints; read-only list/get endpoints still accessible |  | Not Run

## Customer Management
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
CUST-001 | Customers | Critical | Functional | Create customer with valid domestic (UAE) data | Logged in, company context set to a UAE company | 1. Fill name (>=3 chars), tax treatment, place of supply = a UAE emirate 2. Save | name: Acme LLC | Customer created and synced to Zoho if company has zohoOrganizationId |  | Not Run
CUST-002 | Customers | High | Negative | Create customer with name of 2 characters | - | 1. Attempt to create customer with a 2-character name via UI | name: 'Ab' | Confirm whether UI (min 3) and API (schema min 2) agree — test via direct API call with a 2-char name to see which limit actually wins server-side |  | Not Run
CUST-003 | Customers | Critical | Functional | VAT-registered customer requires TRN | - | 1. Select tax treatment = vat_registered 2. Leave TRN blank 3. Save | - | Rejected client + server side — TRN required when requiresTrn flag is true for the treatment |  | Not Run
CUST-004 | Customers | Medium | Edge Case | TRN entered with non-digit characters is silently stripped | - | 1. Enter TRN as 'AE-123-456-7890' 2. Save 3. Reopen record | TRN: AE-123-456-7890 | TRN is silently stored as digits only ('12345667890' etc.) — verify this doesn't surprise/mislead the user; consider whether UI should warn |  | Not Run
CUST-005 | Customers | High | Negative | Duplicate TRN within same company | A customer in Company A already has TRN 123456789 | 1. Create a second customer in Company A with the same TRN | TRN: 123456789 | Rejected — TRN must be unique per company |  | Not Run
CUST-006 | Customers | Medium | Functional | Same TRN allowed across different companies | Customer with TRN X exists in Company A | 1. Create a customer with the same TRN in Company B | TRN: same as above, different company | Allowed — uniqueness is scoped per-company, not global |  | Not Run
CUST-007 | Customers | High | Functional | Non-UAE company: place of supply validation (Saudi org) | Company is the Saudi org (zohoOrganizationId 932531766) | 1. Create VAT-registered customer 2. Set place of supply | place of supply: Saudi Arabia | Accepted only when place of supply = 'Saudi Arabia' for this company (not a UAE emirate) |  | Not Run
CUST-008 | Customers | High | Negative | GCC-treatment customer with invalid country | - | 1. Select gcc_vat_registered treatment 2. Enter a non-GCC country as place of supply | country: 'India' | Rejected — must be one of the 6 GCC country names |  | Not Run
CUST-009 | Customers | Critical | Integration | Customer creation triggers Zoho contact creation before local save | Company has zohoOrganizationId configured, Zoho reachable | 1. Create a new customer | - | Zoho contact created first; local Mongo record saved referencing the new zohoId; verify contact appears in Zoho Books |  | Not Run
CUST-010 | Customers | Critical | Resilience | Customer creation when Zoho API is down/unreachable | Simulate Zoho outage (invalid creds or network block) | 1. Attempt to create a customer | - | Customer is NOT saved locally if Zoho call fails (no orphan/inconsistent record); clear error surfaced to user |  | Not Run
CUST-011 | Customers | High | Edge Case | Process crash between Zoho success and local save | Hard to simulate — flag as manual resilience/chaos test | 1. Kill backend process immediately after Zoho contact creation succeeds but before Mongo save commits | - | Known risk: results in an orphan Zoho contact never linked locally. Verify how support/ops would detect & reconcile this (e.g. via a manual dedupe process) since there's no DB transaction across systems |  | Not Run
CUST-012 | Customers | Medium | Functional | Search customers by name/email/phone | Multiple customers exist | 1. Use search box with partial name | partial string | Matching customers returned; special regex characters in search input are escaped and don't error/leak |  | Not Run
CUST-013 | Customers | Medium | Functional | Export customers to Excel/CSV | Customers exist | 1. Trigger export | - | File downloads with correct company-scoped customer data |  | Not Run
CUST-014 | Customers | High | Integration | Sync customers from Zoho | Company connected to Zoho, some customers exist only in Zoho | 1. Trigger 'sync from Zoho' 2. Monitor progress bar | - | Progress updates via /sync/progress polling; new/changed customers pulled in; unchanged ones skipped (_hasCustomerChanged logic) |  | Not Run
CUST-015 | Customers | Medium | Functional | Cancel an in-progress sync | Sync running | 1. Click cancel mid-sync | - | Sync stops promptly (polled cancellation flag honored between batches); partial results saved so far are consistent |  | Not Run
CUST-016 | Customers | High | Concurrency | Two syncs triggered concurrently for the same company | - | 1. Trigger sync twice in quick succession (two tabs/users) | - | Second attempt should be blocked/queued, not run two overlapping syncs corrupting SyncStateManager's in-memory state |  | Not Run
CUST-017 | Customers | Medium | Edge Case | Two customers in same company with no zohoId | - | 1. Manually create two customers in the same company that both lack a zohoId | - | Both save successfully — verify unique index's partialFilterExpression correctly excludes null/missing zohoId from the uniqueness check |  | Not Run
CUST-018 | Customers | Medium | Functional | Non-VAT-registered customer's TRN field is cleared on save | Customer has a TRN value entered while VAT-registered | 1. Change tax treatment to non_vat_registered 2. Save | - | TRN is cleared per pre-save hook; verify no residual TRN is retained or shown |  | Not Run
CUST-019 | Customers | Medium | Boundary | Email field: empty string handling | - | 1. Save customer with email left blank | email: '' | Empty string is coerced to null (not stored as ''), avoiding false uniqueness collisions between multiple blank-email customers |  | Not Run
CUST-020 | Customers | Low | Functional | Contact person management: add/edit/remove multiple contacts, set primary | - | 1. Add 2+ contactPersons 2. Mark one as isPrimaryContact 3. Save | - | All contacts saved; exactly one primary contact retained |  | Not Run
CUST-021 | Customers | Medium | Functional | TRN expiry date drives deactivation cron | Customer has trnExpiryDate in the past, isActive=true | 1. Wait for/trigger the daily 2am TRN expiry job | - | Customer deactivated locally AND marked inactive in Zoho |  | Not Run
CUST-022 | Customers | High | Negative | TRN expiry job when Zoho call fails | Customer's TRN expired, but Zoho deactivation call fails (network/auth error) | 1. Trigger TRN expiry job with Zoho unreachable | - | KNOWN CODE RISK: job returns early on Zoho failure, so customer stays isActive=true locally despite expired TRN. Confirm this is acceptable or flag as a bug to fix before launch |  | Not Run

## Item Catalog & Sync
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
ITEM-001 | Items/Catalog | Medium | Functional | Search item catalog | Items exist | 1. Search by item name/code | - | Matching items returned |  | Not Run
ITEM-002 | Items/Catalog | High | Integration | Sync items from Zoho | Company linked to Zoho | 1. Trigger item sync 2. Monitor progress | - | Items pulled in/updated; progress bar reflects real status; cache cleared after sync (/clear-cache) |  | Not Run
ITEM-003 | Items/Catalog | Medium | Negative | Create/Update/Delete item via direct API (feature reportedly disabled) | - | 1. Call POST/PUT/DELETE /api/items directly | - | Verify these are properly rejected with a clear 'disabled, managed via Zoho sync' message rather than silently no-op'ing while returning 200 OK (misleading success) |  | Not Run
ITEM-003b | Items/Catalog | Medium | Functional | Add item to a quotation via ItemSelector | Items exist | 1. Search & add an item to a quotation line | - | Item name/price/tax% populate correctly into the line |  | Not Run
ITEM-004 | Items/Catalog | Low | Functional | Item stats dashboard | Items exist | 1. View item stats page | - | Correct counts/aggregates shown |  | Not Run

## Quotation Creation
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
QCR-001 | Quotation Create | Critical | Functional | Create a minimal valid quotation | Logged in as 'user', company+customer exist | 1. New quotation 2. Fill projectName, select company/customer, add 1 item (qty>0, price>=0), set expiryDate 3. Submit | - | Quotation created with status='pending' (non-admin creator); quotationNumber auto-assigned unique per company |  | Not Run
QCR-002 | Quotation Create | Critical | Functional | Admin-created quotation skips ops review | Logged in as admin | 1. Create a quotation as admin | - | initialStatus = 'pending_admin' (bypasses ops_manager queue entirely) — verify it does NOT appear in any ops manager's pending queue |  | Not Run
QCR-003 | Quotation Create | High | Functional | Ops manager creates a quotation for themselves | Logged in as ops_manager | 1. Create a new quotation as ops_manager | - | Verify initial status and confirm it appears correctly under their own 'My Quotations', and doesn't confuse the ops-approval queue (self-approval scenario) |  | Not Run
QCR-004 | Quotation Create | Critical | Negative | Missing required fields rejected | - | 1. Submit with projectName blank / no company / no customer / no expiryDate | - | Each missing field blocked client-side; also verify server rejects if bypassed via direct API |  | Not Run
QCR-005 | Quotation Create | High | Negative | Customer not belonging to selected company | - | 1. Via direct API, submit customerId of a customer belonging to a DIFFERENT company than companyId | mismatched ids | Rejected — server validates the customer belongs to the given company |  | Not Run
QCR-006 | Quotation Create | High | Boundary | Item quantity boundary values | - | 1. Try quantity=0, quantity=-1, quantity=0.0005, quantity=0.001, quantity=1000000 | various | 0 and negative rejected; 0.001 accepted (min per schema); confirm rounding behavior at 0.0005 (rounds to nearest 0.001) |  | Not Run
QCR-007 | Quotation Create | High | Boundary | Item unit price boundary values | - | 1. Try unitPrice=0 (should be valid), unitPrice=-1 (invalid), unitPrice='' or non-numeric (invalid) | 0 / -1 / 'abc' | 0 accepted; negative and non-numeric rejected with clear validation error |  | Not Run
QCR-008 | Quotation Create | Medium | Boundary | Tax% and Discount% boundary values | - | 1. Try 0, 100, 100.01, -1, 150 for both taxPercent and discountPercent via direct API | 150 | 0–100 accepted; values outside range rejected — verify Mongoose ValidationError from schema max:100 is caught and returned as a clean 400, not a raw 500 |  | Not Run
QCR-009 | Quotation Create | High | Negative | Expiry date before creation/query date | - | 1. Set expiryDate earlier than today/creation date | past date | Client-side blocks this; CRITICAL — verify server-side createQuotation also rejects it directly via API (audit found create may be missing the validateDates call that update has) |  | Not Run
QCR-010 | Quotation Create | Medium | Functional | Add multiple items with mixed images | - | 1. Add 3+ items, attach images to some 2. Submit | - | All items saved; images compressed & uploaded to S3 individually |  | Not Run
QCR-011 | Quotation Create | Medium | Resilience | One item image upload fails during creation | Simulate S3 failure for one image (e.g. corrupt/huge file) | 1. Submit a quotation where one image upload fails | - | Quotation still saves successfully; failed image is logged, not fatal — verify user isn't blocked, and check whether they're informed the image didn't attach |  | Not Run
QCR-012 | Quotation Create | Medium | Functional | Add terms & conditions with rich text + embedded images | - | 1. Use the Quill editor, format text, insert an image, add a link 2. Save | - | HTML sanitized both client and server side (sanitizeTermsHtml / sanitizeTerms); malicious tags stripped, formatting/images preserved |  | Not Run
QCR-013 | Quotation Create | Critical | Security | XSS attempt in terms & conditions | - | 1. Insert <script>alert(1)</script> and <img src=x onerror=alert(1)> into the terms editor 2. Save 3. View the rendered quotation/PDF | malicious HTML | Script/onerror payloads are stripped by sanitizeTerms allow-list; no alert fires when viewing |  | Not Run
QCR-014 | Quotation Create | Critical | Security | XSS attempt in plain-text fields (escaped, not sanitized) | - | 1. Enter <script>alert(1)</script> in projectName, item description, contact name, notes 2. Save 3. View quotation/PDF | malicious HTML in plain fields | Rendered as literal escaped text (escapeHtml), not executed |  | Not Run
QCR-015 | Quotation Create | Medium | Edge Case | Unicode / RTL text (Arabic) in customer/project fields | - | 1. Enter Arabic text in projectName and customer contact name 2. Save and view PDF | Arabic text | Displays correctly, right-to-left rendering doesn't break layout, and text isn't mangled/mojibake in the PDF |  | Not Run
QCR-016 | Quotation Create | Low | Boundary | Very long text field values | - | 1. Enter a 5,000+ character string into notes/description fields | long string | Either gracefully truncated with a clear limit, or fully accepted and rendered without breaking layout/PDF pagination |  | Not Run
QCR-017 | Quotation Create | High | Functional | Notify explicit ops managers on submit | - | 1. Submit a quotation choosing specific 'notify manager' emails | selected emails | Only the explicitly selected ops managers receive the submission email, not all ops managers |  | Not Run
QCR-018 | Quotation Create | Medium | Functional | Notify all active ops managers when none explicitly selected | - | 1. Submit a quotation without selecting any specific notify-managers | - | All ACTIVE ops managers receive the email; inactive/deactivated ops managers do not |  | Not Run
QCR-019 | Quotation Create | Medium | Integration | Duplicate contact person (same email+phone) dedupe on submit | Customer already has a contact with the same email+phone as one entered on the quotation | 1. Submit quotation with a 'new' contact matching an existing one | duplicate email+phone | No duplicate contact created locally or in Zoho; existing contact reused (mirrors Zoho's own silent-merge behavior) |  | Not Run
QCR-020 | Quotation Create | Medium | Functional | Quotation number uniqueness per company | - | 1. Create two quotations rapidly for the same company (race condition attempt) | - | Both receive distinct, unique quotationNumbers under the compound companyId+quotationNumber index — no collision even with near-simultaneous creation |  | Not Run

## Quotation Edit-Status
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
QST-001 | Status Transitions | Critical | Functional | Non-admin edits own 'pending' quotation | Creator logged in, quotation status=pending | 1. Edit and resubmit | - | Status remains an editable state per editableStatuses list; changes saved |  | Not Run
QST-002 | Status Transitions | Critical | Negative | Non-admin cannot edit a non-editable-status quotation | Quotation status = approved/awarded/ops_approved | 1. Attempt to edit via API directly as the creator | - | Rejected — editableStatuses gate blocks non-admins outside {pending, ops_rejected, rejected, pending_admin, draft, cancelled, amended} |  | Not Run
QST-003 | Status Transitions | Critical | Functional | Ops manager edits a 'pending' quotation auto-approves it | Ops manager logged in, quotation pending | 1. Ops manager opens and saves an edit (even trivial) on a pending quotation | - | Status flips to 'ops_approved' as a side-effect of editing — verify this is intended UX and clearly communicated to the ops manager (non-obvious behavior, high mis-click risk) |  | Not Run
QST-004 | Status Transitions | High | Functional | Ops manager edits an 'ops_rejected' quotation | Quotation status = ops_rejected | 1. Ops manager edits and saves | - | Status becomes ops_approved per the same rule — confirm this is desired (re-approving after editing a rejected item) |  | Not Run
QST-005 | Status Transitions | High | Functional | Creator edits a 'rejected' quotation | Quotation status = rejected, creator logged in | 1. Creator edits and resubmits | - | Status returns to 'pending' for re-review |  | Not Run
QST-006 | Status Transitions | Critical | Security | Non-creator, non-admin cannot revise a rejected/ops_rejected quotation | Quotation rejected by admin/ops, logged in as a DIFFERENT ops_manager (not creator) | 1. Attempt to edit via API | - | 403 Forbidden — only creator or admin may revise a rejected quotation |  | Not Run
QST-007 | Status Transitions | Critical | Functional | Admin edits a pending/rejected quotation | Admin logged in | 1. Edit any editable-status quotation as admin | - | Status forced to 'pending_admin' after admin's edit |  | Not Run
QST-008 | Status Transitions | High | Functional | Admin edits an approved/awarded/not_awarded quotation | Admin logged in, quotation is approved/awarded | 1. Admin edits line items or terms on an already-approved quotation 2. Save | - | Status remains unchanged (no reset to pending) — CRITICAL: verify totals/approval snapshot data stays internally consistent after this kind of edit, since approval isn't re-triggered |  | Not Run
QST-009 | Status Transitions | Critical | Concurrency | Two ops managers approve the same pending quotation simultaneously | Two ops_manager sessions, one pending quotation | 1. Both click 'ops approve' at nearly the same instant | - | Only one succeeds; the second gets a 409 'status has changed' response (atomic findOneAndUpdate status-guard) — no double-processing/duplicate emails |  | Not Run
QST-010 | Status Transitions | Critical | Concurrency | Admin approves while ops simultaneously edits the same quotation | - | 1. Admin approves at the same moment an ops manager saves an edit to the same record | - | No data corruption or lost update; final state is consistent and one action's result is clearly reflected |  | Not Run
QST-011 | Status Transitions | High | Functional | Image cleanup on edit — orphaned S3 objects removed | Quotation has existing images, edit replaces/removes some | 1. Remove an item image on edit and save 2. Check S3 bucket | - | Orphaned S3 object is deleted; if S3 delete fails, it's only logged (doesn't block the save) — verify no orphan billing/storage buildup over time in practice |  | Not Run
QST-012 | Status Transitions | Medium | Functional | Non-admin deletes own pending quotation | Creator logged in, status=pending or ops_rejected | 1. Delete the quotation | - | Deleted successfully, associated S3 objects cleaned up (best-effort) |  | Not Run
QST-013 | Status Transitions | Critical | Security | Non-admin cannot delete an approved/awarded quotation | Creator logged in, quotation approved | 1. Attempt DELETE via API | - | Rejected — non-admins can only delete pending/ops_rejected quotations |  | Not Run
QST-014 | Status Transitions | Medium | Functional | S3 delete failure during quotation delete doesn't block deletion | Simulate S3 failure | 1. Delete a quotation while S3 is unreachable | - | Quotation record still deleted (Promise.allSettled used); failures logged only |  | Not Run
QST-015 | Status Transitions | Medium | Edge Case | Route ordering: /pdf-metrics not mistaken for an :id | Admin logged in | 1. Call GET /api/quotations/pdf-metrics | - | Returns PDF metrics, NOT a 404/invalid-ObjectId error from being matched against the /:id route — regression-test if routes are ever reordered |  | Not Run

## Approval Workflow
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
APR-001 | Approval Workflow | Critical | Functional | Ops manager approves a pending quotation | Ops manager logged in, quotation pending | 1. Approve | - | Status -> ops_approved; email sent to creator + admins; quotation appears in admin's pending-approval queue |  | Not Run
APR-002 | Approval Workflow | Critical | Functional | Ops manager rejects a pending quotation with reason | Ops manager logged in | 1. Reject, provide a reason | reason text | Status -> ops_rejected; reason stored & shown to creator; email sent to creator |  | Not Run
APR-003 | Approval Workflow | High | Negative | Ops rejection without a reason | - | 1. Attempt to reject without entering a reason | - | Rejected client+server side — reason is required |  | Not Run
APR-004 | Approval Workflow | Critical | Security | Admin-created quotations are invisible to ops managers | Admin created a quotation (status pending_admin) | 1. As ops_manager, check ops queue list 2. Attempt to open it directly by its ID/URL | direct URL to admin-created quotation ID | Does not appear in any ops list; direct GET returns 404 (not 403) — indistinguishable from non-existent, by design |  | Not Run
APR-005 | Approval Workflow | Critical | Functional | Admin approves an ops_approved quotation | Admin logged in, status=ops_approved | 1. Approve | - | Status -> approved; emails sent to creator and ops manager who approved |  | Not Run
APR-006 | Approval Workflow | Critical | Functional | Admin approves a pending_admin quotation (admin-created path) | Admin-created quotation, status=pending_admin | 1. A different admin (or same) approves | - | Status -> approved directly (skips ops layer entirely, consistent with creation logic) |  | Not Run
APR-007 | Approval Workflow | High | Negative | Admin cannot approve from a disallowed status | Quotation status = draft/pending/rejected/awarded | 1. Attempt PUT /approve via API on a non-{ops_approved, pending_admin} quotation | - | Rejected — approve only allowed from ops_approved or pending_admin |  | Not Run
APR-008 | Approval Workflow | Critical | Concurrency | Two admins approve the same quotation simultaneously | Two admin sessions, one ops_approved quotation | 1. Both approve at nearly the same instant | - | Only one succeeds (atomic update + status guard); other gets 409 stale-status error |  | Not Run
APR-009 | Approval Workflow | High | Functional | Admin rejects with reason | Admin logged in | 1. Reject an ops_approved/pending_admin quotation, provide reason | reason | Status -> rejected; reason stored; email sent to creator + ops manager |  | Not Run
APR-010 | Approval Workflow | High | Functional | Self-action email suppression — admin approves own quotation | Admin is both creator and approver | 1. Admin approves their own admin-created quotation | - | No 'approved' notification email sent to self; ops manager notification (if applicable) still sent |  | Not Run
APR-011 | Approval Workflow | Medium | Functional | Self-action email suppression — admin rejects own quotation | Admin is both creator and rejector | 1. Admin rejects their own quotation | - | No rejection email sent to self |  | Not Run
APR-012 | Approval Workflow | Medium | Functional | Admin dashboard stats use base-currency totals | Quotations exist in multiple currencies | 1. View admin dashboard aggregate stats | mixed-currency quotations | Totals shown/aggregated using totalInBaseCurrency (AED), not raw 'total' — verify sums are not currency-mismatched garbage (previously fixed bug area, regression-test it) |  | Not Run
APR-013 | Approval Workflow | Medium | Functional | Ops dashboard stats exclude admin-created quotations | Mix of admin-created and regular quotations exist | 1. View ops dashboard stats as ops_manager | - | Counts/aggregates exclude admin-created (pending_admin-origin) quotations |  | Not Run

## Award & Zoho
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
AWD-001 | Award & Zoho | Critical | Functional | Creator awards an approved quotation (happy path) | Quotation status=approved, company+customer both Zoho-synced, tax rate configured for company/treatment | 1. Creator clicks Award 2. Confirm | - | Zoho estimate created FIRST; only on Zoho success does local status flip to 'awarded' with zohoEstimateId/Number/Url stored; email sent to creator+admins+ops |  | Not Run
AWD-002 | Award & Zoho | Critical | Security | Non-creator cannot award | Logged in as a different user (even admin) than the creator | 1. Attempt PATCH /:id/award via API | - | 403 — only the quotation's creator may award it |  | Not Run
AWD-003 | Award & Zoho | Critical | Negative | Award from a non-approved status | Quotation status = pending/ops_approved/rejected/awarded | 1. Attempt to award | - | Rejected — award only allowed from status='approved' |  | Not Run
AWD-004 | Award & Zoho | Critical | Negative | Award blocked when company not Zoho-synced | Company has no zohoOrganizationId | 1. Attempt to award | - | 422 with code COMPANY_NOT_SYNCED and a clear message |  | Not Run
AWD-005 | Award & Zoho | Critical | Negative | Award blocked when customer not Zoho-synced | Customer has no zohoId | 1. Attempt to award | - | 422 with code CUSTOMER_NOT_SYNCED |  | Not Run
AWD-006 | Award & Zoho | Critical | Negative | Award blocked when tax rate not configured for the org/treatment | Company/tax combo missing from hardcoded TAX_IDS map | 1. Attempt to award | - | 422 with code TAX_RATE_NOT_CONFIGURED — verify this is caught cleanly rather than silently using a wrong org's tax ID (see COMP-007) |  | Not Run
AWD-007 | Award & Zoho | Critical | Functional | 'Not Awarded' path requires no Zoho call | Quotation status=approved | 1. Choose 'Not Awarded' with an optional note | - | Saves immediately with status=not_awarded, no Zoho estimate created; email sent to creator+admins+ops |  | Not Run
AWD-008 | Award & Zoho | Critical | Integration | Domestic (UAE) tax treatment on award | UAE company, domestic customer, VAT registered | 1. Award with standard UAE VAT setup | - | Correct tax ID selected from TAX_IDS map for this org; Zoho estimate total matches local quotation total |  | Not Run
AWD-009 | Award & Zoho | Critical | Integration | GCC customer tax treatment on award | GCC-country customer (not Kuwait/Qatar) | 1. Award a quotation for a GCC customer | - | Correct GCC tax branch applied; verify computed tax on Zoho estimate matches expectation |  | Not Run
AWD-010 | Award & Zoho | High | Edge Case | Kuwait/Qatar customers forced to non_gcc = 0% tax | Customer's country = Kuwait or Qatar | 1. Award a quotation for a Kuwaiti/Qatari customer | - | Tax forced to non_gcc treatment / 0%, regardless of any VAT-registered flag set on the customer |  | Not Run
AWD-011 | Award & Zoho | High | Edge Case | Saudi org uses Saudi Arabia as 'domestic', not UAE | Company zohoOrganizationId = 932531766 (Saudi org) | 1. Award a domestic (Saudi) customer's quotation under this company | - | 'Domestic' place-of-supply logic correctly resolves to Saudi Arabia, not UAE, for tax-branch selection |  | Not Run
AWD-012 | Award & Zoho | Critical | Integration | Discount + tax interaction matrix on Zoho estimate | 4 quotations: {tax=0,disc=0} {tax=0,disc>0} {tax>0,disc=0} {tax>0,disc>0} | 1. Award each of the 4 variants 2. Compare local total vs Zoho estimate total | tax/discount combinations | All 4 cases produce a Zoho estimate total that exactly matches the local quotation total — when tax>0 and discount>0, confirm the discount-baked-into-line-rate approach still reconciles to the same total as the entity-level-discount approach used when tax=0 |  | Not Run
AWD-013 | Award & Zoho | Critical | Resilience | Zoho estimate call times out during award | Simulate slow/unresponsive Zoho endpoint | 1. Attempt award while Zoho times out | - | User sees a clear 'timeout' message; quotation status remains 'approved' (NOT partially awarded); safe to retry |  | Not Run
AWD-014 | Award & Zoho | Critical | Resilience | Zoho returns rate_limit (429) during award | Simulate Zoho 429 response | 1. Attempt award | - | Clear rate-limit message shown; status stays approved; retry succeeds once rate limit clears |  | Not Run
AWD-015 | Award & Zoho | Critical | Resilience | Zoho returns 5xx server_error during award | Simulate Zoho 500/502/503 | 1. Attempt award | - | Clear server-error message; status stays approved; retries happen per backoff policy before giving up |  | Not Run
AWD-016 | Award & Zoho | Critical | Resilience | Zoho auth/token failure during award | Simulate expired/invalid Zoho token that fails to refresh | 1. Attempt award | - | Clear auth-error message; token refresh attempted once; status stays approved on ultimate failure |  | Not Run
AWD-017 | Award & Zoho | Critical | Resilience | Circuit breaker OPEN state during award | Force 5 consecutive Zoho failures beforehand (e.g. 5 failed awards in a row) | 1. Trigger 5 failures 2. Attempt a 6th award within 60s | - | 6th request fails fast with 'circuit_open' kind, without hitting the network; after 60s, a HALF_OPEN probe allows one attempt through |  | Not Run
AWD-018 | Award & Zoho | High | Negative | Zoho client_error (4xx, e.g. malformed payload) during award | Simulate a malformed/rejected payload scenario | 1. Attempt award under this condition | - | Clear client-error message shown; NOT silently retried (client errors aren't retried per circuit breaker logic); status stays approved |  | Not Run
AWD-019 | Award & Zoho | High | Edge Case | Customer deleted/deactivated in Zoho after being locally synced | Customer synced previously, then removed/deactivated directly in Zoho | 1. Attempt to award a quotation for this customer | - | isCustomerGone detection (regex on Zoho error message) surfaces a specific 'customer no longer exists in Zoho, please re-sync' message — verify this detection actually fires for the current real Zoho error wording (fragile regex, worth double-checking against live Zoho) |  | Not Run
AWD-020 | Award & Zoho | Medium | Functional | Currency ID lookup per Zoho org | Company's Zoho org uses a currency | 1. Award a quotation in a non-default currency for this org | - | Correct org-specific currency_id used in the Zoho payload (cached 1hr) rather than a hardcoded/wrong one |  | Not Run
AWD-021 | Award & Zoho | Medium | Resilience | Currency ID lookup fails (non-fatal) | Simulate /settings/currencies call failing | 1. Award a quotation while currency lookup fails | - | currency_id simply omitted from the Zoho payload (logged warning) rather than blocking the whole award |  | Not Run
AWD-022 | Award & Zoho | Critical | Concurrency | Two different companies' quotations awarded simultaneously | Two admin/creator sessions for different companies | 1. Award quotation for Company A and Company B at the same instant | - | Each uses its own correct Zoho org/tax config — no cross-contamination between the two ScopedZohoClient calls (audit flagged this as a high-value concurrency test) |  | Not Run
AWD-023 | Award & Zoho | Medium | Functional | Zoho estimate URL/number stored and clickable | Successful award | 1. After award, view the quotation detail | - | zohoEstimateUrl link opens the correct estimate in Zoho Books; zohoEstimateNumber displayed |  | Not Run

## Cancel-Revise-Amend
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
CXL-001 | Cancel/Revise/Amend | High | Functional | Admin cancels an approved quotation | Admin logged in, status=approved | 1. Cancel with a reason | reason | status -> cancelled, cancelledFromStatus='approved' recorded; reason/actor/timestamp stored |  | Not Run
CXL-002 | Cancel/Revise/Amend | Critical | Security | Ops manager cannot cancel an approved quotation | Ops manager logged in, status=approved | 1. Attempt cancel via API | - | Rejected — only admin can cancel an approved quotation |  | Not Run
CXL-003 | Cancel/Revise/Amend | High | Functional | Admin or ops cancels a pre-approval quotation | Status=pending/ops_approved | 1. Cancel | - | status -> amended (not cancelled, since it wasn't approved yet) — verify UI labels this correctly to avoid confusing 'amended' vs 'cancelled' semantics |  | Not Run
CXL-004 | Cancel/Revise/Amend | High | Negative | Cannot cancel an already-terminal-state quotation | Status = cancelled/amended/awarded/not_awarded | 1. Attempt cancel | - | Rejected for all 4 terminal states with a clear error |  | Not Run
CXL-005 | Cancel/Revise/Amend | Critical | Functional | Revise an approved quotation | Quotation approved | 1. Trigger 'Revise' 2. Edit and resubmit | - | New revision created with revisedFrom set, revisionNumber suffix -R1 applied to quotation number, original marked accordingly |  | Not Run
CXL-006 | Cancel/Revise/Amend | High | Functional | Revise a cancelled quotation whose cancelledFromStatus was 'approved' | Quotation cancelled from an approved state | 1. Trigger revise | - | Allowed — revision path permits this specific case |  | Not Run
CXL-007 | Cancel/Revise/Amend | Critical | Negative | Cannot start a second active revision while one is already in progress | An active (non-cancelled) revision already exists for this original | 1. Attempt to create another revision of the same original | - | 409 conflict — only one active revision allowed at a time |  | Not Run
CXL-008 | Cancel/Revise/Amend | Medium | Functional | Cancel the active revision, then revise again | Active revision exists, then gets cancelled | 1. Cancel the revision 2. Attempt a new revision of the same original | - | Now allowed, since the prior revision is cancelled (no longer 'active') |  | Not Run
CXL-009 | Cancel/Revise/Amend | Medium | Edge Case | Revision numbering strips prior -RN suffix correctly | Quotation is already e.g. QUO-001-R1 | 1. Create another revision from it (after cancelling the prior one) | - | New number becomes QUO-001-R2, not QUO-001-R1-R2 (suffix stripped before re-appending) |  | Not Run
CXL-010 | Cancel/Revise/Amend | Medium | Functional | Editing a cancelled quotation applies revision-on-save | status=cancelled (cancelledFromStatus=approved), creator edits | 1. Edit and save | - | applyRevisionOnSave path triggers correctly, status returns to pending, consistent with CXL-005/006 flows |  | Not Run
CXL-011 | Cancel/Revise/Amend | Medium | Functional | Editing an amended quotation applies amendment-on-save | status=amended | 1. Edit and save | - | applyAmendmentOnSave path triggers, status returns to pending |  | Not Run
CXL-012 | Cancel/Revise/Amend | Low | Functional | Duplicate a quotation | Any existing quotation | 1. Use 'Duplicate' action | - | New draft/pending quotation created with duplicatedFrom set, fresh quotationNumber, items/terms copied but status/approvals NOT carried over |  | Not Run

## Review Comments
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
RC-001 | Review Comments | High | Functional | Ops manager adds a comment on an item description | Quotation pending, ops manager logged in | 1. Highlight text within an item description 2. Add a comment | comment text | Comment saved with targetType='item', anchored via prefix/suffix text match; visible to creator |  | Not Run
RC-002 | Review Comments | High | Functional | Admin adds a comment on terms & conditions text | - | 1. Highlight text in T&C, add comment | - | Comment saved with targetType='terms' |  | Not Run
RC-003 | Review Comments | Medium | Functional | Comment on a header field | - | 1. Highlight header text (e.g. project name), add comment | - | Comment saved with targetType='header' |  | Not Run
RC-004 | Review Comments | High | Functional | Creator resolves a comment | Comment exists, creator logged in | 1. Mark comment resolved | - | Comment flagged resolved; only creator/admin permitted per route rule |  | Not Run
RC-005 | Review Comments | Critical | Security | Non-author, non-admin cannot delete another user's comment | Comment authored by ops_manager A, logged in as ops_manager B | 1. Attempt DELETE via API | - | 403 — only the comment's author or an admin may delete it |  | Not Run
RC-006 | Review Comments | Critical | Security | Only ops/admin can create review comments | Logged in as plain 'user' (creator) | 1. Attempt to POST a comment via API | - | 403 — comment creation restricted to ops/admin roles |  | Not Run
RC-007 | Review Comments | Critical | Edge Case | Comment anchor text is edited/removed after comment was created | Comment anchored to a specific phrase in an item description; creator then edits that description, changing/removing the phrase | 1. Add a comment on text X 2. Creator edits the description removing text X 3. Reload and view comments | - | Verify graceful handling: comment should show as 'orphaned'/unable to relocate rather than crashing the page or mis-highlighting unrelated text |  | Not Run
RC-008 | Review Comments | Medium | Edge Case | Multiple overlapping comments on the same or adjacent text | - | 1. Add 2+ comments on overlapping or immediately adjacent text spans | - | All comments render distinctly without visual overlap corruption or losing one anchor |  | Not Run
RC-009 | Review Comments | Low | Functional | Comment list reflects real-time state across roles | Ops adds a comment while creator has the quotation open | 1. Ops adds comment 2. Creator refreshes/polls | - | Creator sees the new comment (verify whether this requires manual refresh or is live) |  | Not Run

## PDF Generation
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
PDF-001 | PDF Generation | Critical | Functional | Generate PDF for a standard quotation | Any valid quotation | 1. Click 'Download PDF' | - | PDF downloads, opens correctly, starts with %PDF- magic bytes, content matches on-screen preview |  | Not Run
PDF-002 | PDF Generation | High | Regression | VAT line suppressed when tax=0% | Quotation with taxPercent=0 | 1. View PDF | - | VAT row is fully hidden (not shown as '0.00') — recently fixed bug, regression-test it explicitly |  | Not Run
PDF-003 | PDF Generation | High | Regression | Discount line suppressed when discount=0% | Quotation with discountPercent=0 | 1. View PDF | - | Discount row is fully hidden, consistent with the VAT-suppression fix |  | Not Run
PDF-004 | PDF Generation | High | Functional | VAT and discount both shown when both > 0 | taxPercent=5, discountPercent=10 | 1. View PDF | - | Both lines shown with correct calculated amounts |  | Not Run
PDF-005 | PDF Generation | High | Boundary | Currency decimal places — 2 vs 3 decimal currencies | Create quotations in AED (2dp) and KWD/BHD/OMR (3dp) | 1. Generate PDF for each | amount: 123.456 | AED/SAR/QAR/USD/EUR/GBP show 2 decimals; KWD/BHD/OMR show 3 decimals consistently across summary, items, and amount-in-words |  | Not Run
PDF-006 | PDF Generation | Medium | Boundary | Multi-page item list — exact page-break boundary | Quotation with exactly ITEMS_PER_FIRST_PAGE items, then one more, one fewer | 1. Generate PDF for N-1, N, N+1 items (N = the constant's value) | - | Page breaks correctly; totals row appears exactly once, on the correct (last) page |  | Not Run
PDF-007 | PDF Generation | Medium | Edge Case | Very large item count (50+) | Quotation with 50+ line items | 1. Generate PDF | - | Renders without timeout/crash; pagination remains correct throughout |  | Not Run
PDF-008 | PDF Generation | Critical | Security | Injected script/HTML in free-text fields does not execute in PDF | Quotation with <script> in projectName/description/notes | 1. Generate PDF | - | Rendered as literal escaped text via escapeHtml, no script execution risk in the Puppeteer render context |  | Not Run
PDF-009 | PDF Generation | Medium | Edge Case | Unicode/Arabic/RTL text in PDF | Quotation with Arabic customer/contact names | 1. Generate PDF | - | Correct font rendering, no mojibake, RTL text doesn't break layout |  | Not Run
PDF-010 | PDF Generation | Medium | Edge Case | Item with multiple images (2-per-row grid) | Item has 3+ images | 1. Generate PDF | - | Images render in a 2-per-row grid without overflow/overlap |  | Not Run
PDF-011 | PDF Generation | Medium | Resilience | Broken/expired S3 signed URL for an image | One image's signed URL has expired | 1. Generate PDF | - | That image is silently omitted (caught .catch() -> null, filtered out); rest of the PDF still generates successfully |  | Not Run
PDF-012 | PDF Generation | Low | Functional | Approval-chain footer hides 'Reviewed By' for admin-created quotations | createdByRole='admin' | 1. View PDF for an admin-created (ops-skipped) quotation | - | Ops/'Reviewed By' column/row is cleanly omitted, no misaligned table |  | Not Run
PDF-013 | PDF Generation | Medium | Boundary | Amount-in-words for large, zero, and fractional totals | Totals: 0, 1,234,567.89, 0.5 | 1. Generate PDF for each | - | numberToWords produces grammatically correct English for all three cases |  | Not Run
PDF-014 | PDF Generation | High | Performance | Concurrent PDF generation load test | - | 1. Trigger 5+ simultaneous PDF downloads (different quotations/users) | - | First 3 (PDF_MAX_CONCURRENT default) process immediately; remainder queue (up to 50) and complete; beyond queue timeout (30s) returns a clear 503 'queue full/timed out' rather than hanging |  | Not Run
PDF-015 | PDF Generation | Medium | Resilience | Puppeteer/Chromium crash recovery | Simulate killing the headless Chromium process mid-generation | 1. Force a browser disconnect during a PDF request 2. Immediately request another PDF | - | Shared browser instance auto-relaunches on 'disconnected' event; subsequent requests succeed without requiring a server restart |  | Not Run
PDF-016 | PDF Generation | Medium | Functional | Browser print path matches server PDF path | Same quotation | 1. Use in-browser Print (window.print via hidden iframe) 2. Compare to the server-generated PDF | - | Both use buildPDFHTML and should match closely; note and flag any font/margin/pagination discrepancies between browser print and headless Chromium rendering |  | Not Run
PDF-017 | PDF Generation | Medium | Functional | Item/terms/internal-doc image compression pipeline | Upload large images (e.g. 5MB photos) to each of the 3 image types | 1. Upload and save 2. Inspect resulting stored image size/dimensions | 5MB source images | Item images capped ~800px/70%/300KB, terms ~600px/65%/200KB, internal docs ~1000px/75%/400KB — verify quality remains acceptable and PDF generation stays fast |  | Not Run

## Email Notifications
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
EML-001 | Email Notifications | Critical | Functional | Submission email to ops managers on create | Non-admin creates a quotation (status becomes pending) | 1. Create quotation 2. Check ops managers' inboxes | - | creatorSubmittedNotifyOps email received by the correct recipients (explicit list or all active ops managers) with a working deep link to the quotation |  | Not Run
EML-002 | Email Notifications | High | Functional | Ops approval emails | Ops approves a pending quotation | 1. Approve 2. Check creator's and admins' inboxes | - | opsApprovedNotifyCreator + opsApprovedNotifyAdmins both received |  | Not Run
EML-003 | Email Notifications | High | Functional | Ops rejection email with reason | Ops rejects with a reason | 1. Reject 2. Check creator's inbox | - | opsRejectedNotifyCreator received, includes the rejection reason |  | Not Run
EML-004 | Email Notifications | High | Functional | Admin approval emails | Admin approves | 1. Approve 2. Check creator's and ops manager's inboxes | - | adminApprovedNotifyCreator + adminApprovedNotifyOpsManager both received |  | Not Run
EML-005 | Email Notifications | High | Functional | Admin rejection email | Admin rejects with reason | 1. Reject 2. Check inboxes | - | adminRejectedNotifyCreator + adminRejectedNotifyOpsManager received, includes reason |  | Not Run
EML-006 | Email Notifications | High | Functional | Award/Not-awarded emails to all stakeholders | Quotation awarded or marked not-awarded | 1. Award / Not-award 2. Check creator + all admins + all ops managers' inboxes | - | quotationAwardedNotifyAll / quotationNotAwardedNotifyAll received by everyone except the actor themself (deduplicated) |  | Not Run
EML-007 | Email Notifications | High | Functional | Self-action suppression verified end-to-end | Admin approves/rejects/awards their own quotation | 1. Perform each self-action 2. Check admin's own inbox | - | Admin does NOT receive a notification email about their own action; other relevant parties (ops) still do |  | Not Run
EML-008 | Email Notifications | Medium | Functional | Email deep links route correctly per role | Any notification email | 1. Click the 'view quotation' link from an email 2. Observe destination | - | Lands on the correct quotation with action=review&for=<role> context, and role-appropriate UI (e.g. approve/reject buttons) is shown if the recipient is logged in with that role |  | Not Run
EML-009 | Email Notifications | Critical | Security | HTML-escaping of interpolated values in email templates | Create a quotation/customer with <script> or special HTML chars in name/project fields | 1. Trigger any notification email 2. Inspect raw email HTML source | malicious HTML | All interpolated values are escaped (esc()); no script injection or broken HTML in the rendered email |  | Not Run
EML-010 | Email Notifications | Critical | Resilience | Missing/invalid Azure Graph credentials — silent no-op | Simulate missing AZURE_* env vars in a staging environment | 1. Trigger any action that fires an email | - | Underlying action (approve/reject/award) still succeeds; a warning is logged server-side; NO error is surfaced to the end user even though the email never sent — explicitly verify prod credentials are valid before go-live, since this failure mode is invisible to users |  | Not Run
EML-011 | Email Notifications | Medium | Resilience | Graph API 429 rate limit — retry honors Retry-After | Simulate a 429 response with Retry-After header | 1. Trigger an email send under this condition | - | Retries after the specified delay, up to 3 attempts, eventually succeeds or gives up silently without blocking the underlying action |  | Not Run
EML-012 | Email Notifications | Medium | Resilience | Graph API 401 — token refreshed and retried once | Simulate an expired Graph token | 1. Trigger an email send | - | Cached token invalidated, fresh token obtained, single retry attempted |  | Not Run
EML-013 | Email Notifications | Medium | Resilience | Graph API network timeout — gives up silently after 3 attempts | Simulate persistent network timeout to Graph API | 1. Trigger an email send | - | 3 attempts with 2s/4s backoff, then gives up without throwing — confirm the calling action (e.g. approve) still returns success to the user |  | Not Run
EML-014 | Email Notifications | Low | Functional | Concurrent email sends share one Azure token refresh | Multiple emails fire in quick succession (e.g. award notifying many recipients) | 1. Trigger an action that fires several emails near-simultaneously | - | Only one token refresh call made (mutex/shared promise), not one per email |  | Not Run
EML-015 | Email Notifications | Medium | Gap-Check | Creator submission confirmation email | Non-admin creates a quotation | 1. Create a quotation 2. Check the CREATOR's own inbox for a confirmation | - | KNOWN CODE GAP: submissionConfirmedToCreator template exists but doesn't appear to be called anywhere. Confirm with stakeholders whether creators are expected to get a 'submission received' email — if yes, this is a bug to fix before launch |  | Not Run

## Currency & Exchange
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
CUR-001 | Currency/Exchange | High | Functional | Live exchange rate fetch and conversion | open.er-api.com reachable | 1. Create a quotation in a foreign currency 2. Verify conversion to base currency (totalInBaseCurrency) | e.g. USD -> AED | Conversion uses the current live rate; totalInBaseCurrency stored accurately |  | Not Run
CUR-002 | Currency/Exchange | High | Resilience | Exchange rate API down, cached rate available | Mongo-cached rate exists within its 3600s TTL | 1. Simulate open.er-api.com being unreachable 2. Create/view a quotation needing conversion | - | Falls back to the cached rate seamlessly; totals remain correct |  | Not Run
CUR-003 | Currency/Exchange | Critical | Resilience | Both live API and cache unavailable — hardcoded fallback table | No cache entry, API down | 1. Simulate full outage 2. Create a quotation | - | Falls back to the hardcoded AED_TABLE; totals stay sane (no NaN/zero totals); verify the fallback numbers are still reasonably current at go-live time |  | Not Run
CUR-004 | Currency/Exchange | Medium | Functional | Admin manually refreshes exchange rates | Admin logged in | 1. Trigger /rates/refresh | - | Rates updated from live source, cache TTL reset |  | Not Run
CUR-005 | Currency/Exchange | Medium | Gap-Check | Hourly exchange rate cron actually running in production | - | 1. Check server logs/cron scheduler in the deployed environment for exchangeRateJob execution | - | KNOWN CODE GAP: exchangeRateJob does not appear to be wired into server.js startup (only trnExpiryJob is). Confirm whether rates are only ever refreshed lazily on-demand, or whether this cron needs to be added before launch to avoid stale cached rates |  | Not Run
CUR-006 | Currency/Exchange | Medium | Functional | Company acceptedCurrencies restricts selector options | Company configured with a specific subset of acceptedCurrencies | 1. Create a quotation for this company 2. Open currency selector | - | Only the company's accepted currencies are selectable, not all 9 supported currencies |  | Not Run
CUR-007 | Currency/Exchange | Medium | Boundary | Currency conversion rounding consistency | - | 1. Convert/enter an amount that produces a long decimal (e.g. 100 / 3.6725) | 100 / 3.6725 | Rounded consistently to 3 decimal places per the Mongoose setter across item price/total fields, no floating-point drift accumulating across many line items |  | Not Run

## In-App Notifications
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
NOTIF-001 | In-App Notifications | Medium | Functional | Notification created and shown in bell/drawer | Trigger any of the 12 notification types (sync_completed, quotation_submitted, etc.) | 1. Perform the triggering action 2. Check notification bell/drawer | - | Notification appears with correct type/priority; unread count increments |  | Not Run
NOTIF-002 | In-App Notifications | High | Gap-Check | Approval/rejection/award events produce in-app notifications, not just email | Approve/reject/award a quotation | 1. Perform each action 2. Check the affected users' notification bell | - | KNOWN CODE GAP FLAGGED BY AUDIT: verify whether in-app Notification docs are actually created for these events, or whether only emails fire currently (schema defines the types but the emitting code path wasn't confirmed) — decide before launch whether this is acceptable or needs fixing |  | Not Run
NOTIF-003 | In-App Notifications | Medium | Functional | Mark single notification as read | Unread notification exists | 1. Click/open it | - | Marked read; unread count decrements |  | Not Run
NOTIF-004 | In-App Notifications | Low | Functional | Mark all as read | Multiple unread notifications | 1. Click 'mark all read' | - | All marked read; count -> 0 |  | Not Run
NOTIF-005 | In-App Notifications | Low | Functional | Archive / delete a notification | Notification exists | 1. Archive then delete | - | Removed from active list appropriately |  | Not Run
NOTIF-006 | In-App Notifications | Low | Boundary | Auto-expiry after 30 days | Notification older than 30 days (TTL index) | 1. Wait/simulate TTL expiry | - | Notification auto-removed by MongoDB TTL index |  | Not Run

## Security & Resilience
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
SEC-001 | Security & Resilience | Critical | Security | IDOR — access another user's quotation by guessing/incrementing ID | Logged in as a regular user with no relation to a target quotation | 1. Call GET /api/quotations/:id for a quotation not created by / not visible to this user | other user's quotation ID | 403/404 as appropriate — no data leakage of another user's/company's quotation |  | Not Run
SEC-002 | Security & Resilience | Critical | Security | Cross-company data isolation via companyContext | User has access to Company A only (if such restriction exists) or via x-company-id header manipulation | 1. Attempt to fetch Company B's customers/quotations by manipulating the x-company-id header/query | spoofed company id | Confirm what access model actually applies (are all authenticated users allowed to see all companies, or is there per-user company restriction?) — verify actual behavior matches intended design |  | Not Run
SEC-003 | Security & Resilience | Critical | Security | SharedQuotation component authorization | - | 1. Access the shareable/public quotation view route without logging in | direct URL | Verify explicitly whether this route is intentionally public (read-only, no sensitive data) or requires auth — audit flagged this as unverified; confirm no accidental data exposure |  | Not Run
SEC-004 | Security & Resilience | High | Security | Regex injection in search endpoints | - | 1. Enter regex special characters in customer/quotation search (e.g. `.*`, `(`, `[`) | .*¦(){}[] | Input is escaped (escapeRegex) before use in MongoDB queries; no error, no unintended broad matches, no ReDoS |  | Not Run
SEC-005 | Security & Resilience | High | Security | Puppeteer PDF endpoint trusts caller-supplied HTML | Authenticated user | 1. Attempt to submit crafted HTML with SSRF-style external resource references (e.g. <img src='http://internal-service/...'>) to /generate-pdf | crafted HTML | Confirm the sandboxed page truly blocks non-image network requests (stylesheet/font/media/script/xhr/websocket) as designed; verify image requests can't be abused for SSRF against internal services |  | Not Run
SEC-006 | Security & Resilience | High | Security | File upload validation bypass (internal documents) | - | 1. Attempt to upload a file exceeding MAX_DOCUMENT_SIZE_MB or with a disallowed MIME type via direct API (bypassing client validation) | oversized file / .exe file | Server-side rejects — confirm size/type limits are enforced server-side, not just client-side in quotationUtils.js |  | Not Run
SEC-007 | Security & Resilience | Medium | Security | Committed Zoho token file | - | 1. Check backend/.zoho-token.json in the deployed repo/build | - | Should NOT contain real production tokens committed to version control; verify .gitignore covers it and rotate any token that was ever committed |  | Not Run
SEC-008 | Security & Resilience | High | Security | Rate limiting on global API (600 req/min/IP) | - | 1. Send a burst exceeding 600 req/min from one IP | - | Requests beyond the limit are throttled (429), protecting against basic DoS/scraping |  | Not Run
SEC-009 | Security & Resilience | Medium | Security | Body size limit enforcement (25MB) | - | 1. Submit a request with a payload larger than 25MB (e.g. many large uncompressed images) | - | Rejected cleanly (413) rather than crashing the server or hanging |  | Not Run
SEC-010 | Security & Resilience | High | Concurrency | SyncStateManager in-memory state under multi-instance/cluster deployment | Production runs PM2 in cluster mode (check ecosystem.config.js) | 1. Trigger a sync 2. Verify progress polling/cancel works correctly if requests land on different PM2 worker processes | - | KNOWN CODE RISK: SyncStateManager is in-memory/per-process, so progress/cancel may behave inconsistently across worker processes or after a restart — confirm actual deployment topology and test accordingly; recommend sticky sessions or a shared store if cluster mode is used |  | Not Run
SEC-011 | Security & Resilience | Medium | Security | CORS allow-list enforcement | - | 1. Attempt an API request from an origin NOT on the configured allow-list | foreign origin | Request blocked by CORS; verify the allow-list matches exactly the production frontend domain(s), no wildcard left over from dev |  | Not Run
SEC-012 | Security & Resilience | Medium | Security | Helmet security headers present | - | 1. Inspect response headers on any API call | - | Standard security headers (CSP/X-Frame-Options/etc. per helmet defaults or custom config) are present |  | Not Run
SEC-013 | Security & Resilience | Low | Performance | Large quotation list pagination/performance | 1000+ quotations exist for a company | 1. Load 'My Quotations' / admin quotation list | - | List loads within acceptable time via pagination/lean queries; auto-populate doesn't cause an N+1 slowdown at this scale |  | Not Run
SEC-014 | Security & Resilience | Medium | Security | Password fields never returned in API responses | - | 1. Inspect GET /auth/me and any user list/detail responses | - | password, passwordResetToken, passwordResetExpires never present in JSON (select:false enforced) |  | Not Run

## Mobile & Cross-Browser
Test ID | Module | Priority | Type | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Notes
RESP-001 | Mobile & Cross-Browser | High | UI/UX | Desktop vs mobile quotation layout parity — pricing/VAT | Same quotation viewed on desktop and mobile widths | 1. View a quotation with tax+discount on desktop (QuotationLayout.jsx) 2. View the same quotation on a mobile viewport (MobileQuotationLayout.jsx) | - | Totals, VAT, discount, and currency formatting match exactly between the two independently-maintained renderers |  | Not Run
RESP-002 | Mobile & Cross-Browser | Medium | UI/UX | Desktop vs mobile — multi-page item lists | Quotation with 20+ items | 1. View on both desktop and mobile | - | Both handle pagination/scrolling sensibly without losing/duplicating items |  | Not Run
RESP-003 | Mobile & Cross-Browser | Medium | UI/UX | Desktop vs mobile — terms & conditions images render | T&C contains embedded images | 1. View on both layouts | - | Images render correctly sized on both, no broken image icons |  | Not Run
RESP-004 | Mobile & Cross-Browser | Medium | UI/UX | Core flows usable on a real mobile device/small viewport | - | 1. Create, edit, approve, and award a quotation using a mobile viewport (not just resized desktop browser) | - | All primary actions are reachable and usable (no cut-off buttons/modals) on common mobile screen sizes |  | Not Run
RESP-005 | Mobile & Cross-Browser | Medium | UI/UX | Cross-browser smoke test | - | 1. Run core flows (login, create, approve, award, PDF download) in Chrome, Safari, and Firefox | - | No layout breakage or JS errors specific to a given browser; PDF download works in all three |  | Not Run
RESP-006 | Mobile & Cross-Browser | Low | UI/UX | Sync progress modal on mobile | Trigger a customer/item sync | 1. Open sync progress modal on a mobile viewport | - | Progress bar and cancel button remain usable/visible |  | Not Run